iCARE++

Module-Based Development Work Plan

Batangas State University – TNEU ARASOF Nasugbu

Linux Adona  ·  Andre Cachola  ·  Xyreel Laguras  |  June 15 – July 24, 2026

How This Plan Works

The project is broken into six independent modules. Each module runs its own sprint sequence — development begins only when its dependencies are ready. Every sprint has a single sprint goal, a backlog of user stories with story point estimates, and a checkbox column for real-time tracking during standups.

Sprint Calendar

| Module | W1 Jun 15–21 | W2 Jun 22–28 | W3 Jun 29–Jul 5 | W4 Jul 6–12 | W5 Jul 13–19 | W6 Jul 20–24 |
| --- | --- | --- | --- | --- | --- | --- |
| Frontend | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 |  |  |
| Backend | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 |  |  |
| ML / AI |  | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 |  |
| Mobile | Sprint 1 |  | Sprint 2 | Sprint 3 | Sprint 4 |  |
| Analytics | Sprint 1 |  |  | Sprint 2 |  | Sprint 3 |
| Testing |  |  |  |  | Sprint 1 | Sprint 2 |

Frontend   Module

Owner: Linux Adona     Next.js web application — UI/UX, component library, state management, and responsive design.

Sprint 1   Week 1  ·  7 story points

| Sprint Goal | Produce approved wireframes and scaffold the Next.js project with routing and base layout components. |
| --- | --- |

| ID | User Story / Task | Owner | Pts | Status |
| --- | --- | --- | --- | --- |
| FE-01 | Create wireframes for all major screens (dashboard, quiz, records, analytics) | Linux | 3 | ☐ |
| FE-02 | Initialize Next.js project, folder structure, and Tailwind/design tokens | Linux | 2 | ☐ |
| FE-03 | Build base layout: nav bar, sidebar, page shell | Linux | 2 | ☐ |

Sprint 2   Week 2  ·  8 story points

| Sprint Goal | Develop all primary page components and wire routing so the app is fully navigable. |
| --- | --- |

| ID | User Story / Task | Owner | Pts | Status |
| --- | --- | --- | --- | --- |
| FE-04 | Build Dashboard, Student Profile, and Records pages | Linux | 3 | ☐ |
| FE-05 | Build Quiz page and Recommendation result view | Linux | 3 | ☐ |
| FE-06 | Build Analytics/Reports page skeleton | Linux | 2 | ☐ |

Sprint 3   Week 3  ·  8 story points

| Sprint Goal | Integrate live API data and global state management; implement authentication UI flow. |
| --- | --- |

| ID | User Story / Task | Owner | Pts | Status |
| --- | --- | --- | --- | --- |
| FE-07 | Set up global state (Context/Zustand) and API service layer | Linux | 3 | ☐ |
| FE-08 | Connect all pages to live REST API responses | Linux | 3 | ☐ |
| FE-09 | Build login/register screens and auth redirect guards | Linux | 2 | ☐ |

Sprint 4   Week 4  ·  6 story points

| Sprint Goal | Polish the UI — full responsiveness, loading states, error handling, and cross-browser checks. |
| --- | --- |

| ID | User Story / Task | Owner | Pts | Status |
| --- | --- | --- | --- | --- |
| FE-10 | Apply responsive breakpoints across all pages | Linux | 2 | ☐ |
| FE-11 | Add loading skeletons, empty states, and error boundaries | Linux | 2 | ☐ |
| FE-12 | Cross-browser and accessibility review + fixes | Linux | 2 | ☐ |

Backend   Module

Owner: Linux Adona     Node.js REST API — database schema, endpoints, authentication, and API documentation.

Sprint 1   Week 1  ·  7 story points

| Sprint Goal | Lock the database schema and define all API endpoint contracts before any code is written. |
| --- | --- |

| ID | User Story / Task | Owner | Pts | Status |
| --- | --- | --- | --- | --- |
| BE-01 | Design and finalize relational database schema (ERD) | Linux | 3 | ☐ |
| BE-02 | Define REST API contract: all endpoints, methods, request/response shapes | Linux | 2 | ☐ |
| BE-03 | Initialize Node.js project, ORM setup (Prisma/Sequelize), and DB connection | Linux | 2 | ☐ |

Sprint 2   Week 2  ·  7 story points

| Sprint Goal | Implement and test core CRUD endpoints with a seeded live database. |
| --- | --- |

| ID | User Story / Task | Owner | Pts | Status |
| --- | --- | --- | --- | --- |
| BE-04 | Implement CRUD endpoints for Users, Students, and Records | Linux | 3 | ☐ |
| BE-05 | Implement CRUD for Quiz, Clinical, and Analytics entities | Linux | 3 | ☐ |
| BE-06 | Seed database with realistic test data | Linux | 1 | ☐ |

Sprint 3   Week 3  ·  7 story points

| Sprint Goal | Secure all endpoints with JWT auth and validate inputs. API is production-hardened. |
| --- | --- |

| ID | User Story / Task | Owner | Pts | Status |
| --- | --- | --- | --- | --- |
| BE-07 | Implement JWT authentication and role-based authorization middleware | Linux | 3 | ☐ |
| BE-08 | Add input validation, rate limiting, and error handling middleware | Linux | 2 | ☐ |
| BE-09 | Write Postman/Swagger API documentation for all endpoints | Linux | 2 | ☐ |

Sprint 4   Week 4  ·  6 story points

| Sprint Goal | Expose ML/AI prediction endpoints and ensure the full API is integration-ready. |
| --- | --- |

| ID | User Story / Task | Owner | Pts | Status |
| --- | --- | --- | --- | --- |
| BE-10 | Expose ML model prediction endpoint (calls Python service) | Linux | 2 | ☐ |
| BE-11 | Expose AI Clinical Decision Support endpoint | Linux | 2 | ☐ |
| BE-12 | End-to-end API smoke test with frontend and mobile clients | Linux | 2 | ☐ |

ML / AI   Module

Owner: Linux Adona     Student Performance Prediction ML model, AI Clinical Decision Support module, and Adaptive Quiz Recommendation Engine.

Sprint 1   Week 2  ·  9 story points

| Sprint Goal | Collect, clean, and explore the dataset to confirm it supports the prediction target. |
| --- | --- |

| ID | User Story / Task | Owner | Pts | Status |
| --- | --- | --- | --- | --- |
| ML-01 | Gather historical student academic and clinical data | Linux | 2 | ☐ |
| ML-02 | Clean, normalize, and handle missing values in dataset | Linux | 3 | ☐ |
| ML-03 | Exploratory data analysis (EDA) — feature correlation review | Linux | 2 | ☐ |
| ML-04 | Set up clinical data pipeline for AI Decision Support module | Linux | 2 | ☐ |

Sprint 2   Week 3  ·  11 story points

| Sprint Goal | Train a baseline ML model and build the AI rule engine logic. |
| --- | --- |

| ID | User Story / Task | Owner | Pts | Status |
| --- | --- | --- | --- | --- |
| ML-05 | Feature engineering and train/test split | Linux | 2 | ☐ |
| ML-06 | Train candidate models (Random Forest, XGBoost, etc.) and compare metrics | Linux | 3 | ☐ |
| ML-07 | Build AI Clinical Decision Support rule engine (logic + conditions) | Linux | 3 | ☐ |
| ML-08 | Build quiz bank taxonomy and tag question difficulty levels | Xyreel | 3 | ☐ |

Sprint 3   Week 4  ·  13 story points

| Sprint Goal | Tune and finalize all models; implement the adaptive recommendation algorithm; integrate all modules. |
| --- | --- |

| ID | User Story / Task | Owner | Pts | Status |
| --- | --- | --- | --- | --- |
| ML-09 | Hyperparameter tuning and final model evaluation (F1, accuracy, AUC) | Linux | 3 | ☐ |
| ML-10 | Integrate AI rule engine with clinical data pipeline | Linux | 2 | ☐ |
| ML-11 | Build quiz recommendation algorithm (collaborative/content-based filtering) | Xyreel | 3 | ☐ |
| ML-12 | Build adaptive scoring logic (difficulty adjustment based on responses) | Linux | 3 | ☐ |
| ML-13 | Wrap all models as Python microservice / REST endpoints | Linux | 2 | ☐ |

Sprint 4   Week 5  ·  7 story points

| Sprint Goal | Validate all AI/ML outputs against real scenarios; close the feedback loop on the quiz engine. |
| --- | --- |

| ID | User Story / Task | Owner | Pts | Status |
| --- | --- | --- | --- | --- |
| ML-14 | Clinical review of AI Decision Support recommendations | Linux | 2 | ☐ |
| ML-15 | End-to-end quiz engine testing: simulate student sessions | Xyreel / Andre | 3 | ☐ |
| ML-16 | Validate ML predictions against held-out test set; log metrics | Linux | 2 | ☐ |

Mobile   Module

Owner: Linux Adona     React Native (Expo) mobile application — UI, navigation, API integration, and offline mode.

Sprint 1   Week 1  ·  4 story points

| Sprint Goal | Produce mobile wireframes and initialize the Expo project with navigation scaffolding. |
| --- | --- |

| ID | User Story / Task | Owner | Pts | Status |
| --- | --- | --- | --- | --- |
| MOB-01 | Design mobile wireframes for all core screens | Linux | 2 | ☐ |
| MOB-02 | Initialize Expo project, Expo Router tabs, and global style tokens | Linux | 2 | ☐ |

Sprint 2   Week 3  ·  7 story points

| Sprint Goal | Build all core screens with navigation fully working on device/emulator. |
| --- | --- |

| ID | User Story / Task | Owner | Pts | Status |
| --- | --- | --- | --- | --- |
| MOB-03 | Build Home, Dashboard, Quiz, and Records screens | Linux | 3 | ☐ |
| MOB-04 | Build Profile, Notifications, and Settings screens | Linux | 2 | ☐ |
| MOB-05 | Implement tab and stack navigation (Expo Router) | Linux | 2 | ☐ |

Sprint 3   Week 4  ·  8 story points

| Sprint Goal | Connect the mobile app to the live API and implement offline caching. |
| --- | --- |

| ID | User Story / Task | Owner | Pts | Status |
| --- | --- | --- | --- | --- |
| MOB-06 | Integrate all screens with REST API via service layer | Linux | 3 | ☐ |
| MOB-07 | Implement offline mode with AsyncStorage/MMKV caching | Linux | 3 | ☐ |
| MOB-08 | Handle auth token storage and auto-refresh on mobile | Linux | 2 | ☐ |

Sprint 4   Week 5  ·  7 story points

| Sprint Goal | Test on real devices (iOS + Android), fix platform-specific bugs, and finalize the build. |
| --- | --- |

| ID | User Story / Task | Owner | Pts | Status |
| --- | --- | --- | --- | --- |
| MOB-09 | Test on Android physical device and emulator; log issues | Andre | 2 | ☐ |
| MOB-10 | Test on iOS simulator; fix platform-specific UI differences | Andre | 2 | ☐ |
| MOB-11 | Fix all critical and high-priority mobile bugs | Andre | 3 | ☐ |

Analytics   Module

Owner: Xyreel Laguras     Data warehouse, ETL pipeline, analytics dashboard, and report/export features.

Sprint 1   Week 1  ·  5 story points

| Sprint Goal | Design the data warehouse architecture and define the schema for analytics tables. |
| --- | --- |

| ID | User Story / Task | Owner | Pts | Status |
| --- | --- | --- | --- | --- |
| AN-01 | Design warehouse schema: fact and dimension tables | Xyreel | 3 | ☐ |
| AN-02 | Choose warehouse technology (PostgreSQL schema / BigQuery / DuckDB) and set up | Xyreel | 2 | ☐ |

Sprint 2   Week 4  ·  10 story points

| Sprint Goal | Build the ETL pipeline and render the first working dashboard with live data. |
| --- | --- |

| ID | User Story / Task | Owner | Pts | Status |
| --- | --- | --- | --- | --- |
| AN-03 | Build ETL pipeline: extract from operational DB, transform, load to warehouse | Linux | 3 | ☐ |
| AN-04 | Schedule ETL runs (cron / event-driven) and add error logging | Linux | 2 | ☐ |
| AN-05 | Build dashboard UI with charts: student performance, clinical trends | Linux | 3 | ☐ |
| AN-06 | Connect dashboard to warehouse queries via API | Linux | 2 | ☐ |

Sprint 3   Week 6  ·  7 story points

| Sprint Goal | Complete report generation and export features; finalize the dashboard for handoff. |
| --- | --- |

| ID | User Story / Task | Owner | Pts | Status |
| --- | --- | --- | --- | --- |
| AN-07 | Implement PDF/Excel report generation from dashboard data | Xyreel | 3 | ☐ |
| AN-08 | Add date range filters, drill-down views, and export buttons | Xyreel | 2 | ☐ |
| AN-09 | Final dashboard QA: data accuracy check against source DB | Xyreel | 2 | ☐ |

Testing   Module

Owner: Andre Cachola     System integration testing, performance benchmarking, bug triage/resolution, and regression sign-off.

Sprint 1   Week 5  ·  12 story points

| Sprint Goal | Execute the full integration test suite and generate the performance benchmark report. |
| --- | --- |

| ID | User Story / Task | Owner | Pts | Status |
| --- | --- | --- | --- | --- |
| QA-01 | Write and run module integration test cases (all inter-module flows) | Andre | 3 | ☐ |
| QA-02 | Execute end-to-end scenario tests (student journey, clinical flow, quiz session) | Andre | 3 | ☐ |
| QA-03 | Set up k6/JMeter; run load and response-time benchmarking tests | Andre | 2 | ☐ |
| QA-04 | Run throughput and concurrency tests; generate benchmark report | Andre | 2 | ☐ |
| QA-05 | Triage all found bugs: assign priority (Critical / High / Low) | Andre | 2 | ☐ |

Sprint 2   Week 6  ·  9 story points

| Sprint Goal | Resolve all critical and high bugs; complete regression testing; achieve sign-off. |
| --- | --- |

| ID | User Story / Task | Owner | Pts | Status |
| --- | --- | --- | --- | --- |
| QA-06 | Fix all Critical and High priority bugs | Andre | 3 | ☐ |
| QA-07 | Fix UI/UX and minor functional issues | Andre | 2 | ☐ |
| QA-08 | Run full regression test suite on fixed areas | Andre | 3 | ☐ |
| QA-09 | Team sign-off review — confirm build is stable and deployment-ready | All | 1 | ☐ |